MINUTES OF A HOYLAKE FORUM MANAGEMENT COMMITTEE MEETING HELD ON 24 FEBRUARY 2014
Present:	Peter Edwards (PE)	Mark Howard (MH)	Rose Kirkby (RK),	Richard Stowe (RS)	Vaughan Williams (VW)	Stewart Lowther (SL)
Chris Moore (CM)

Apologies:	Matthew Biagetti (MB)	Cllr Gerry Ellis (GE)	Cllr John Hale (JH),
Jackie Hall (JaH)	John Percival (JP),

ITEM 1. APOLOGIES / Apologies for non-attendance were noted. / ITEM 2. MINUTES OF PREVIOUS MEETING / Minutes of the meeting on 14 January 2014 were agreed. The following matters arose: / Beach Management. SL now understood that ecological management of the beach was vested in the Marine Conservation Agency whereas Wirral Council had responsibility for the amenity aspects. / Town Centre Action Plan. The Council was expected to issue an amended TCAP for Hoylake having received comments from its consultation exercise. / Proposed Arts Centre. There continued to be commercial and private interest in the proposed Arts Centre. Discussions were continuing. / Proposed Health Trail/Outdoor Gym. HVL had lodged an application for partial funding from the Wirral West Public Health Grants Programme for an outdoor health trail/gym to enhance the Promenade. / ITEM 3. NEIGHBOURHOOD PLAN / Latest Draft Neighbourhood Plan. SL had updated the draft NP and this was now ready for further advice from Locality. CM agreed to submit a draft for “Figure 3. Special Buildings and Places” to complete the document. / Locality Grant & Assistance. The earlier meeting with Ms Carol Latham of Planning Aid had been extremely helpful. She had carefully explained the pathway, processes and responsibilities to achieve the Referendum. She had provided us with a NP project management tool and some examples of completed project plans. There was a need to: / Establish a review period for the NP, if adopted: five years was suggested. / Harmonise the Hoylake NP with existing and emerging Council strategies and policies as far as possible. / Keep a careful record of all deliberations and consultations and how comments had been assessed and/or incorporated. / Consult the Council to agree time scales and submission dates. / Submit the draft Plan to NPIERS (Neighbourhood Planning Inspectorate) for an advisory health check (comments likely within 2 weeks of submission). / Subsequently, submit the NP to the Council to allow the mandatory consultation period of six weeks to be initiated. Consultation was required with a number of statutory bodies as well as the affected residents, community groups and businesses. / HV (with Planning Aid assistance) to coordinate and arrange public information events and documents to allow full consultation. / Provide a Consultation Statement at the end of the period explaining the consultation process achieved throughout the evolution of the plan. / Formally submit the plan to the Council for scrutiny by an Examiner to be chosen jointly by the Council and HV. / Council Role. From that stage forward, the Council bore main responsibility for publication of the plan, consideration of the Examiner's report and decision, publication of pre-referendum information and documents, arranging the referendum and publication of the result. To these ends, it was agreed to have an early meeting with the Council officer concerned (John Entwistle) to ensure clear mutual understanding. / Timetable. From the information available to date a possible timetable might be: / NPIERS Health Check by 31 March / Incorporation of recommended amendments by 4 April / Submission to Wirral Council for statutory consultations 4 April / Mandatory minimum 6 week Consultation period to 16 May / Assessment of Consultation & preparation of Statement by 30 May / Production of final publicity material by Council by 27 June / Earliest date for Referendum 25 July / In practice, it seems likely that slippage would occur and that the best and most realistic date for the Referendum would be in the autumn. / 7. Engagement With Other Groups. In order to better deliver the plan, it was agreed that there would be great merit in engaging with other community groups to increase knowledge and to ensure that everybody shared a sense of ownership of the plan under a possible tag line of “Taking Charge of Our Future” or similar. Arising from Item 5 (below), there was now an opportunity for recruitment of an energetic extra committee member to assist in driving the further consultations and delivery of the plan. There was also a clear role for the Ward Councillors in supporting and promoting greater knowledge of the plan. A full range of media outlets should be used including a billboard campaign which had been so successful for the “What's Your Vision” campaign. / ITEM 4. FUTURE MEETINGS / 8. The next Committee meeting was scheduled for 18.30 on Monday 24 March at The Parade Community Centre. / ITEM 5. OTHER BUSINESS / 9. In view of Mr John Percival's inability both for business and health reasons to have attended committee meetings and to play a part in delivery of the plan it would be established whether he could continue as a committee member but remain a Forum member. / C T MOORE 10 March 2014 / HV Hon Sec	Action / SL / ALL / CM